## Use Case Template
Project Title: GymQuest Release #: 0.9 Sprint #: 6
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that <outcome> | Estimate | Assigned To
1 | User Registration | As a User | I want to register an account | so that I can get a username and password | 4 | Eric
1 | User Login | As a User | I want to log in | so that I can access my account and workout routines. | 4 | Eric
2,3 | Create Workout Routine | As a User | want to create a workout routine | so that I can plan my exercises for the week. | 8 | Eric
5 | Log Workout | As a User | want to log my workout | so that I can keep track of my progress. | 8 | Eric
9 | View Workout History | As a User | I want to view my workout history | so that I can see my progress over time. | 6 | Eric
4 | Start Routine | As a User | I want to start a routine based on today's date | so that I can follow my planned workout. | 6 | Eric
9 | Personal Records | As a User | I want to see my personal records | so that I can stay motivated. | 6 | Eric
7 | End Workout Session | As a User | I want to end my workout session | so that I can see a summary of my performance. | 4 | Eric
8 | Edit Profile | As a User | I want to edit my profile | so that I can update my personal information. | 6 | Eric
11 | Add exercises to existing routine | As a User | I want to add exercises to an existing routine | so that I can change my routine if I desire | 3 | Eric
12 | Edit exercises of existing routine | As a User | I want to edit exercises of an existing routine | so that I can change my routine if I desire | 3 | Eric
13 | Remove exercises from existing routine | As a User | I want to remove exercises of an existing routine | so that I can change my routine if I desire | 3 | Eric
14 | Enhanced UI/UX | As a User | I would like an appealing user interface | so that I have a positive user experience | 6 | Eric
15 | Cardio feature | As a User | I would like to be able to add cardio exercises to my routine | so that I can track cardio performance | 6 | Eric
16 | Exercise database population | As a Developer | I would like to seed the database with many exercises | so that I can test a large array of data | 2 | Eric
14 | Add AJAX to every user interaction | As a User | I would like a responsive user interface | so that I know when my interactions have been recognized by the application | 6 | Eric
15 | Add Oauth | As a User | I would like to be able to log in using my google account | so that I can log in with a 1 click | 4 | Eric